## Comparison to original scope
Draft 2025 BCWMC Plan Update Schedule (draft 3/1/2022) |  | Gray cells = original scope; colored cells = current projected schedule
|  | Stakeholders |  |  |  | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
Phase | Task (within Phase) | Commission | City staff | Agencies | Public | time axis 2022-01-01 to 2026-12-01
Phase 1 - Initial Stakeholder Engagement | Developing a stakeholder engagement plan | X |  | X | bar: 2022-03-01 to 2022-04-01
| Notification letter & summary of responses |  | X | X | bar: 2022-04-01 to 2022-07-01
| BCWMC TAC issues discussions | X | X | bar: 2022-04-01 to 2022-05-01
| Commission kickoff and issue discussion | X | bar: 2022-06-01 to 2022-07-01
| Hosting diversity, equity and inclusion event | X | X |  | X | bar: 2022-02-01 to 2022-04-01
| Hosting an online survey and summary |  |  |  | X | bar: 2022-07-01 to 2022-12-01
| Meeting with community members | X |  |  | X | bar: 2022-07-01 to 2022-09-01
| Engage the public at community/partner events | X | X |  | X | bar: 2022-07-01 to 2022-12-01
| Hosting public kickoff/initial planning meeting | X | X | X | X | bar: 2023-02-01
| Establishing & meeting with Plan TAC |  | X | X | bar: 2023-03-01; 2023-06-01 to 2023-07-01; 2023-10-01 to 2023-12-01; 2024-03-01; 2024-06-01 to 2024-07-01; 2025-01-01 to 2025-02-01
| Commissioner issue priority workshop | X | bar: 2023-03-01 to 2023-04-01; 2023-08-01
Subtotal
Phase 2 - Pre-Plan Work to Address Challenges | Preliminary gaps analysis | X | bar: 2022-04-01 to 2022-05-01
| Scope pre-plan work to address challenges* | X | X | bar: 2022-05-01 to 2022-07-01
| Perform pre-plan work to address challenges* | X | X | bar: 2022-07-01 to 2023-10-01
Subtotal
Phase 3 - Develop the Draft Plan Development | Update Physical Environment Inventory | X | X | bar: 2023-01-01 to 2023-07-01
| Defining issues and measurable goals | X | X | X | bar: 2023-05-01 to 2024-12-01
| Revising policies and performance standards | X | X | X | bar: 2023-10-01 to 2024-02-01; 2024-10-01 to 2025-02-01
| Creating a targeted implementation program | X | X | X | bar: 2024-02-01 to 2024-08-01; 2025-01-01 to 2025-05-01
| Compiling the complete draft plan | X | X | bar: 2024-09-01 to 2024-12-01; 2025-06-01 to 2025-08-01
Subtotal
Phase 4 - Review and Approval | Formal review; draft responses and get Comm. approval | X | X | X | X | bar: 2024-12-01 to 2025-03-01; 2025-09-01 to 2025-12-01
| Distributing responses and hosting public hearing | X |  |  | X | bar: 2025-04-01; 2025-12-01
| Revising the Plan for 90-day review | X | bar: 2025-03-01 to 2025-05-01; 2025-11-01 to 2026-01-01
| 90-day review |  |  | X | bar: 2025-06-01 to 2025-08-01; 2026-01-01 to 2026-03-01
| Obtaining BWSR Approval (subcommittee meeting) |  |  | X | bar: 2025-08-01; 2026-03-01
| BCWMC Adoption and Plan Production/Distribution | X | bar: 2025-09-01; 2026-04-01
Subtotal
X = notable meeting dates (e.g., DEI summit, Plan adoption)
* = larger challenges include chloride regulations, diversity/equity/inclusion considerations, linear project standards, CIP process, and education program

## Updated Schedule
Draft Plan Schedule - Updated November 26, 2024 |  | TAC |  |  | PSC |  |  | Comm |  |  | BWSR/Plan TAC
|  | 2024 |  |  | 2025 | [35 empty] | 2026
Task | Plan Section | Dec PSC | Dec TAC | Dec Comm | Jan PSC | Jan Plan TAC | Jan Comm | Feb PSC | Feb TAC | Feb Comm | Mar PSC | Mar TAC | Mar Comm | Apr PSC | Apr Plan TAC | Apr Comm | May PSC | May Plan TAC | May Comm | Jun PSC | Jun TAC | Jun Comm | Jul PSC | Jul TAC | Jul Comm | Aug PSC | Aug TAC | Aug Comm | Sep PSC | Sep TAC | Sep Comm | Oct PSC | Oct TAC | Oct Comm | Nov PSC | Nov TAC | Nov Comm | Dec PSC | Dec TAC | Dec Comm | Jan PSC | Jan TAC | Jan Comm | Feb PSC | Feb TAC | Feb Comm | Mar PSC | Mar TAC | Mar Comm | Apr PSC | Apr TAC | Apr Comm | May PSC | May TAC | May Comm | Jun PSC | Jun TAC | Jun Comm | Jul PSC | Jul TAC | Jul Comm | Aug PSC | Aug TAC | Aug Comm | Sep PSC | Sep TAC | Sep Comm | Oct PSC | Oct TAC | Oct Comm | Nov PSC | Nov TAC | Nov Comm | Dec PSC | Dec TAC | Dec Comm
Plan intro / past accomplishments | Intro
Finalize Goals per Comm workshop | Issues & Goals
Complete issues narrative | Issues & Goals
Format issues narrative in InDesign | Issues & Goals
Implementation narrative | Implementation
Chloride actions | Implementation
Linear Standards | Req. Doc? Imp?
Buffers | Req. Doc? Imp?
"Other" Requirements Doc changes | Req. Doc? Imp?
Implementation schedule (non CIP) | Implementation
CIP updates (and prioritization) | Implementation
Plan TAC to review goal buckets 3/4 | Goals and Issues
Plan TAC to review implementation | Implementation
Compile Plan doc from pieces (InDesign) | NA
Plan executive summary (InDesign?) | NA
Monitoring Plan | Appendices
Education/Engagement Plan | Appendices
60 day review | NA
Revise plan per review | NA
Publie hearing | NA
90 day submittal | NA
Adoption | NA
[20 empty] | PSC review full draft plan |  |  | PSC review revised full draft plan & Exec Summary |  | Internal review; presented to Commission at workshop | PSC review Commission feedback |  | Commission sees final "draft", authorizes submittal; assume workshop not needed | [6 empty] | PSC reviews 60-day comments, staff recom responses & plan revisions, directs staff to revise |  |  | PSC reviews revisions |  | Comm reviews revisions, hearing, authorize submittal |  |  |  | No BWSR board meeting in February, delaying offical approval to March |  |  |  |  | BWSR board meets the 4th Wednesday of the month
Note on AN28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We may be able to skip this step (or have to, depending on required hearing date) Reply: Possible, but I don’t want to assume that the PSC won’t want to look at potentially-significant revisions before it goes to the full Comm.
Note on AP28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm timing of this - should it be earlier? Reply: This could potentially be moved up a month if comments are minor and PSC doesn’t want to see edits beforehand (just proposed responses)